COUNTY OF SOLANO 2011 PUBLIC SAFETY REALIGNMENT ACT IMPLEMENTATION PLAN UPDATE October 2014

The recommendations and opinions that are contained in this independent Report are those of the author, and may not reflect the views of the individual members of the Executive Committee of the Community Corrections Partnership.

TABLE OF CONTENTS

SECTION											PAGE

Introduction											  1

2011 Plan Review:

Component 1:  Risk and Needs Assessment					  4

Component 2:  Community Supervision						  9

Component 3:  Alternatives to Custody						12

Component 4:  Intermediate Sanctions						15

Component 5:  Custody and In-Custody Programs				18

Component 6:  Reentry								18

Component 7:  Service Delivery Strategies						27

Implementation Element 1:  Training							30

Implementation Element 2:  Communication					32

Implementation Element 3:  Evaluation and Quality Control			33

Conclusion											35

Recommendations Summary								36

References											39

Appendices

INTRODUCTION

In July 2012, the Community Corrections Partnership (CCP) approved a recommendation to enter into contract with Thomas White, a Corrections Consultant to provide support to the CCP and design the programmatic framework for the County’s Centers for Positive Change (CPC).  At the CCP meeting held on February 26, 2014 the CCP approved a recommendation to have Mr. White “conduct an independent review, and make recommendations to the CCP on any changes or revisions necessary to enhance the goals” of the County of Solano 2011 Public Safety Realignment Act Implementation Plan.

The Public Safety Realignment Act of 2011 expanded the role and purpose of the Community Corrections Partnership (CCP) which was previously established in Penal Code Section 1230 through SB 678 and pursuant to AB 117 an Executive Committee of the CCP is required to prepare an AB 109 Implementation Plan that will enable each county to meet the goals of the Public Safety Realignment legislation.  The legislation requires a local collaborative planning and implementation process which emphasizes community-based corrections, intermediate sanctions and punishment, use of evidence-based practices / programs, and improved supervision strategies.  Further, the legislation states “The purpose of justice reinvestment is to manage and allocate criminal justice populations more cost effectively, generating savings that can be reinvested in evidence-based strategies that increase public safety while holding offenders accountable.”

Evidence-based practices are based on five primary principles.  These principles address the questions of who, what, and how to apply the most effective correctional interventions.  If followed, research shows that evidence-based practices and programs are effective in reducing recidivism.  Evidence-based correctional planning should incorporate the following:

- The Risk Principle (who):  Target resources to higher risk offenders.  Ideally, sufficient resources would be applied to supervise, case manage and treat high and moderate risk offenders appropriately.

- The Need Principle (what):  Apply interventions that target each offender’s particular criminogenic needs.  Criminogenic needs are those areas that are dynamic (can be changed) and have been scientifically demonstrated to be correlated with likelihood of re-offense.  The criminogenic needs that most strongly predict recidivism are antisocial cognition (thoughts and beliefs) that support antisocial behavior; antisocial temperament, which is often characterized by poor decision making skills, anger management difficulties, and impulse control deficits; and antisocial associates (Andrews & Bonta, 2010).  Other dynamic risk factors that to a lesser degree influence crime include family/marital stress, substance abuse, employment instability, educational attainment and engagement difficulties, and lack of prosocial leisure activities.  Research shows that interventions that target these criminogenic needs consistently lead to superior outcomes (Andrews & Bonta, 2010).

- The Responsivity Principle (how):  Interventions should be applied based on the individual characteristics of offenders that may affect how they may respond to the given intervention.  Such characteristics include mental health issues, medical issues, intelligence level, readiness for change, etc.

- The Treatment Principle (how):  The most effective correctional interventions are behavioral, focusing on factors that influence behavior, are action-oriented, and are appropriately reinforced.  These include cognitive-behavioral approaches that provide structured social learning where new skills and behaviors are taught and modeled.

- The Fidelity Principle (how):  Evidence-based programs must be implemented as designed, often including structured measurements of model-adherence, extensive quality assurance mechanisms, pre- and post-evaluation, and other methodologies for ensuring fidelity.

The Solano County 2011 Implementation Plan’s recommended actions focused on “maximizing public safety, enhancing necessary infrastructure, and expanding the criminal justice and human service practices and services which research indicates are essential for reducing offender recidivism.”

It is with the above goals and principles as a guide that this review was conducted.  To begin the process the Consultant reviewed the 2011 Plan and prepared a document which identified the primary actions and recommendations that were included in the Plan as approved by the CCP Executive Committee.  In April the document was sent to key County Agencies (Probation Department, Sheriff’s Office, Health and Social Services, District Attorney’s Office, and the Public Defender’s Office) asking them to provide an update on the implementation of those actions and recommendations.  (See Appendix A).  Based upon the information received by the above agencies, coupled with follow-up contacts and meetings with other community stakeholders, the following review and report was developed.  The Report format will first list the Component identified in the 2011 Plan, followed by one or more of the approved actions / recommendations; an implementation update; and when deemed appropriate a discussion of future recommendations.

2011 PLAN REVIEW

Component 1:  Risk and Needs Assessment

- Risk and needs assessments, as well as additional specialized assessments which may be necessary, such as those to identify mental health and/or substance abuse issues, will be used to guide the development and implementation of individualized case plans which may be refined and revisited over time.

Implementation Update

For all clients placed on probation, including Post Release Community Supervision (PRCS) and 1170 clients, the Probation Department has implemented a comprehensive assessment and case planning protocol.  Each client within their first 30 days of placement on Probation is administered five individual assessments.  The Level of Service Case Management Inventory (LS/CMI) is a validated risk and needs assessment instrument that identifies each client’s risk to recidivate as well as identifying the primary criminogenic needs or risk factors that have contributed to the client’s criminal behavior.  This instrument also guides the determination of the level of supervision that the client will initially be placed on.  The Adult Substance Use Survey Revised (ASUS-R) is an instrument which helps to determine the client’s involvement in substance abuse; any potential mental health issues; the client’s motivation and readiness to address any identified substance abuse problems; and the type or dosage of treatment that should be considered.  The Correctional Mental Health Screen (CMHS) is a gender specific tool that supplements the ASUS-R by identifying clients who may have a serious mental health problem.  The Basic Needs Screen (BNS) helps determine if the client has any issues that should be addressed to both improve their quality of life, and increase the likelihood that they will attend any needed treatment.  The final assessment is the What I Want To Work On Questionnaire which identifies what the client believes are the problems in their life and the degree of importance for them to address each problem.  In addition to these assessments, clients placed on probation who are registered sex offenders are also administered specialized sex offender assessments the Static-99R and the STABLE-2007.  These assessments along with the client’s Court ordered conditions are used to develop, in collaboration with each client, an individualized Case Plan which will guide the client’s activities while they are on probation supervision.  The Case Plan is a living document which is regularly reviewed with the client and modified as circumstances dictate.

The Sheriff’s Office is currently preparing to pilot the LS/CMI for use within the jail.  This information will be used to assess suitability for the Alternatives to Custody Program for sentenced inmates, to inform inmate placement into programming options, and to prepare for the reentry planning process.

Use of the LS/CMI by the Sheriff’s Office will allow for sharing of offender information between the Sheriff’s Office and the Probation Department and will help reduce some duplication of work related to offender assessment.

Health and Social Services (HSS) substance abuse and mental health counselors are also using the ASUS-R and concurrent toxicity screening, as well as the DSM 5 in concordance with trauma screening.  For the female population, clinicians use the gender specific assessment tool “Women’s Risk and Needs Assessment (WRNA)”.

Recommendations and Discussion

The LS/CMI is a criminal risk and needs assessment that produces a risk to recidivate score, identifies the client’s risk factors that are associated with their criminal behavior and the client’s corresponding criminogenic needs.  It is not meant to be used as a pretrial release screen and when administered should be supplemented by a mental health and substance abuse assessment.  Therefore, to achieve the Sheriff’s Office objective of assessing an inmate’s suitability for the ATC program, informing placement into appropriate programming, and supporting the development of an inmate reentry plan, more than the LS/CMI should be administered.  I would recommend that a mental health screen and a substance abuse screen also be completed as soon as possible after the inmate has been placed in the jail.  Although there are a number of validated mental health and substance abuse screens, I recommend using the Correctional Mental Health Screen and the Texas Christian University Drug Screen.  Both are brief assessments that can be administered at no cost.  Copies of these screens can be found in Appendix B.

The LS/CMI and the ASUS-R are robust assessment tools that have been validated and normed to national criminal populations.  Although they have proven to be predictive throughout the United States, they should be validated and normed to a representative sample of offenders residing in Solano County.  Because both tools are automated within the Probation Department, the data that would be needed is capable of being collected and analyzed.  Either in-house researchers or local Universities should be able to carry out such a project once there is a representative sample size.

Assessment tools that are completed following a formal interview with the offender (like the LS/CMI) are only as accurate as the person conducting the interview and scoring the assessment.  At a minimum given the same information, staff, when completing the tools, should be getting close to the same scores.  To ensure there is congruency between staff who are administering the LS/CMI inter-rater reliability tests need to be conducted at least on an annual basis.

Agencies using the LS/CMI should set up a process to ensure that staff, when given the same offender information, are properly scoring the assessment. Inter-rater reliability was included in the initial training that Probation staff received on the LS/CMI.  However, the Probation Department needs to conduct annual inter-rater reliability testing beginning with the Court Unit, and followed by all staff who conduct LS/CMI reassessments.

Finally, the LS/CMI is a general risk and needs assessment and for some offenders, it should be supported by a specialized offender type risk assessment.  This is particularly the case when assessing sex offenders and domestic violence offenders.  Presently the Probation Department does use two specialized sex offender assessments but has not yet implemented a specialized domestic violence risk screen.  Therefore I would recommend that a brief risk screen be administered to all probationers convicted of domestic violence.  The results of the screen coupled with the results of the LS/CMI should inform the intensity of probation supervision.  Further information on one such screen has been included in Appendix C.

- Probation will provide the risk / needs information generated by assessment to the Court after arraignment and before an individual’s readiness conference.  It will also provide the Court with assessment information relevant to alternatives to custody and terms and conditions of probation targeting criminogenic needs.

Implementation Update

At the present time, the information obtained through administering the LS/CMI is being incorporated into the majority of Presentence Investigation Reports (not prior to arraignment) when a sentence of probation is statutorily possible.  Recently the Probation Department requested and was authorized 4 positions to establish a Pretrial Services Program for Solano County.  A Pretrial Committee, comprised of representatives from the District Attorney’s Office, the Public Defender’s Office, the Sheriff’s Office, and the Probation Department has been established.  The Committee has been tasked with developing the policy and procedures for the County’s Pretrial Services Program, and guides the implementation of the Program in late 2014.  The Committee has selected the Ohio Pretrial Risk Assessment tool to use as the risk screen, and is in the process of developing the Program’s operational procedures.

Recommendations and Discussion

Pretrial Services Programs have been operating within the United States for over five decades.  The success of these programs resulted in Congress passing a major overhaul of the Federal bail statute in 1966.  These statutory changes meant that risk, not money, should dictate who should be released during the pretrial period and how.  Further revisions required that in addition to the risk of Failure to Appear in Court, judicial officials were also required to consider the risk that each defendant posed to the safety of the community.

Current pretrial research commissioned by the Laura and John Arnold Foundation (LJAF) has demonstrated how critical the earliest decisions made in the criminal justice system may be for public safety, fairness, and cost-effectiveness.  This robust multi-year research included the following findings:  (See Appendix D)

- Defendants who were detained for the entire pretrial period were over four times more likely to be sentenced to jail and over three times more likely to be sentenced to prison than defendants who were released at some point pending trial.  Furthermore their sentences were significantly longer, almost three times as long for defendants sentenced to jail, and more than twice as long for those sentenced to prison.

- Even for relatively short periods behind bars, low and moderate risk defendants who were detained for more days were more likely to commit additional crimes in the pretrial period, and were also more likely to do so during the two years after their cases ended.

- There was no indication that detaining high risk defendants for longer periods before trial lead to a greater likelihood of pretrial criminal activity.

- Low-risk defendants held for 2-3 days were 22% more likely to fail to appear in Court than similar defendants (in terms of criminal history, charge, background, and demographics) held for less than 24 hours.  The number jumped to 41 percent for defendants held 15-30 days.  For low-risk defendants held for more than 30 days, the study found a 31 percent increase in Failure to Appear.

- There was no impact of pretrial confinement on high-risk defendant’s rates of missing court, and for moderate-risk defendants, the effect was minimal.

It is now becoming apparent that public safety is increased when low and selected moderate risk defendants are not detained while awaiting the disposition of their cases.  Therefore, a well-designed pretrial services program is in the best interest of the public and the defendants.

The Pretrial Justice Institute which was founded in 1977 has identified six core functions of a pretrial services program that were derived from national standards.  In developing a pretrial program for Solano County, these standards should be followed as closely as possible:

- Impartial universal screening of all defendants regardless of charge.

- Verification of interview information and criminal history checks.

- Assessment of risk of pretrial misconduct through objective means and presentation of recommendations to the Court based upon the risk level.

- Follow-up reviews of defendants unable to meet the conditions of release.

- Accountable and appropriate supervision of those released, to include proactive court date reminders.

- Reporting on process and outcome measures to stakeholders.

Component 2:  Community Supervision

- Intake and assessment of PRCS will include initial contact prior to release from prison whenever possible, assistance with applications for services, risk and needs assessment, and connection to community support.

Implementation Update

Probation staff sends reporting instructions and Special Conditions of PRCS clients to the California Department of Correctional Rehabilitation (CDCR) upon notice of release.  Then the client reports to the Probation Department for the initial appointment where a comprehensive assessment of risk/needs is conducted.  Given the challenges associated with the geographical location of the prisons throughout the State, Probation has been unable to conduct face-to-face meetings and provide assistance to clients prior to release from prison.  However, for the Jail population under realignment (1170), Probation staff travel to the local jail to complete the assessments prior to release, and if in need of immediate services, are referring to and beginning treatment services before release to the community.

- Probation’s caseload ratio for high-risk supervision of 1 officer to 50 active probationers will be maintained for the PRCS and 3/non-offenders.

Implementation Update:

Probation has implemented a client case classification and supervision model that uses the client’s level of risk and corresponding intensity of supervision to establish work units for determining an individual probation officer’s caseload size.  The single level caseload goal for high-risk clients is 45.  Manageable caseloads are best determined by a combination of client risk and established supervision standards as opposed to any arbitrary caseload number.  The majority of PRCS and 1170 (3/non-offenders) clients are being assessed as high-risk and at the present time, the caseloads of the probation officers supervising these clients are manageable as determined by their individual work units.

- Probation is developing training for trainers in Intermediate Level MI to further advance use of this proven practice.  It is noteworthy too, that MI and the assessment tools, come with built-in quality control, as they are both subject to ongoing review and quality improvement.

Implementation Update

During Fiscal Year 2011-2012 and 2012-2013, Solano County Probation had all of their staff complete six 4-hour sessions of Intermediate Motivational Interviewing (MI) Training.  This was done by in-house instructors.  During Fiscal Year 2013-2014, all new staff received twelve hours of Introduction to MI and then 12 hours of Intermediate MI training.  Each class member was coached on one tape utilizing their MI skills prior to the Intermediate course.  In addition, Deputy Supervising Probation Officers are required to listen to each of their staff on a quarterly basis while interacting with a client and provide coaching and feedback on the officer’s use of MI.  Neither MI nor the Assessments “come with built-in quality control.”  They are however, “both subject to ongoing review and quality improvement” for the staff administering the Assessments and using MI.

Recommendations and Discussion:

Motivational Interviewing (MI) has proven to be an effective approach for probation officers to use with clients to help facilitate positive behavior change.  As indicated above, the Probation Department has provided its staff with multiple trainings in Motivational Interviewing.  The training primarily consisted of theory and discussion coupled with skill demonstration, followed by opportunities for the trainees to practice the skills in role play situations and receive feedback.  Research has indicated that classroom training using the above teaching methods resulted in only five percent (5%) of the trainees using the new skills in their jobs, (Joyce and Showers, 2002).  However when the individuals who received the training were provided coaching and feedback on the skills taught while they were in their work setting, use of the skills jumped to 96%, (Joyce and Showers, 2002).  The author of Motivational Interviewing, William Miller, observed similar results when teaching MI (Miller and Mount, 2001).  For MI skills to be sustained, the newly learned skills need to be supported when interacting with clients.  The most efficient way to accomplish this is to have a trained coach provide feedback to the staff person by listening with them to an audio recording of their interaction with a client.  This process would need to continue for a significant period of time for most staff to acquire proficiency in MI.  This is also the case for staff trained in Effective Practices In Community Supervision (EPICS), another research informed model that the Solano County Probation Department has provided training in for staff working with probation clients.  Although some feedback to staff has been provided by EPICS trained coaches, at this point it lacks the frequency and duration that for most staff is required to ensure skill acquisition.  A full time coach who has been trained in both MI and EPICS would be a sound investment for the County and the Probation Department.

- Community supervision programming for realigned offenders will use the principles of another evidence-based practice, Cognitive Behavioral Therapy (CBT).

The Probation Department has implemented a research informed model of probation supervision for all realigned offenders.  Supportive policies have been issued and staff have received training in both policy requirements, as well as the supervision skills necessary for effective implementation.  The three day training in Effective Practices In Community Supervision (EPICS), included staff training in a Cognitive Behavioral Therapy (CBT) model that staff can use with their clients.  In addition the Probation Department has incorporated a number of CBT programs for realigned offenders within the County’s Centers for Positive Change (CPC) to include the following:

- Unlock Your Thinking and Open Your Mind

- The Courage to Change

- Thinking for a Change

- Reasoning and Rehabilitation II

Component 3:  Alternatives to Custody

- The Sheriff, working with justice system partners, has developed an Alternatives to Custody (ATC) Program for pre-adjudicated offenders designed to manage the population of unsentenced, low to medium risk offenders currently being housed in the jail.  The ATC will allow those awaiting trial and/or sentencing to be conditionally released from custody and, in lieu of incarceration, be supervised in the community by the Probation Department or the Sheriff’s Office.

Sentenced offenders are subject to the Sheriff’s Office Alternatives to Custody which include Home Detention with Electronic Monitoring (EM) and a Global Positioning Satellite (GPS) program.

Implementation Update

The Sheriff’s Office has not yet implemented the release of any AB-109/1170 inmates awaiting trial or sentenced, to an Alternative to Custody Program.  The addition of jail bed space and the number of new admissions has at this point not required the implementation of this Program.  The Sheriff’s Office fully supports the development of a Pretrial Services Program that will be run by the Probation Department.  For non-AB-109/1170 offenders who are placed in the jail, the Sheriff’s Office does operate a comprehensive Alternative to Custody Program (ATC).  ATC staff conducts a thorough background investigation on each applicant to determine eligibility and assess any apparent threat to the community or likelihood of re-offense.  During this process, the facts of prior and convicted offenses are carefully evaluated. Past criminal history (domestic violence, etc.), institutional misconduct, failure to appear, and/or non-compliance with Probation or Parole terms are also taken into consideration during this evaluation.  Once approved, participants pay a daily fee for each day on the program.  The daily fee is determined from two sources (equipment costs and one and a half times the participant’s hourly rate).  If an applicant is unable to pay all or a portion of the fees, a procedure is in place to allow for reduced or waived fees.  Participants are not turned away due to an inability to pay.  ATC Officers meet with program participants each week, ensuring compliance to employment and school schedules, curfew and program rules, as well as conducting random drug testing.

Random home compliance checks are performed on the residence of ATC participants by the Sheriff’s Enforcement Team (SET) and the ATC Supervisor.  These random checks reinforce the integrity of the program, encourage participant compliance, and provide additional safety to the community.  In addition to the random compliance checks performed, when issues arise with ATC clients, SET team members are alerted and have the ability and knowledge regarding program rules and equipment to respond promptly and efficiently.

On a rotating basis, an ATC Officer is assigned on-call duty which makes them available after office hours, weekends and holidays for participants to contact in case of an emergency.  The On-Call Officer is responsible for the status of all electronic home detention participants and must respond to program violators or equipment issues.  The Sheriff supports the On-Call Officer with the patrol division for the retaking of program violators into custody.

All participants must abide by California State Law, Probation terms, and Court orders.  Participants must adhere strictly to no weapons possession; abstain from use of and possession of alcohol, use of and possession of illegal drugs and/or paraphernalia in addition to agreeing to random drug testing.  Participants who live with other adults, must have those individuals sign a tenant agreement explaining the “no alcohol, illegal drugs or weapons allowed” policy.  Participants who are found to be in violation of the terms and conditions of this program are subject to verbal counseling, loss of errand time, program termination and/or new criminal charges being filed.

The Sheriff’s Alternative to Custody Program consists of the potential for offender participation in the following programs:

- Work Furlough – Approved applicants are housed in the custody of the Sheriff and allowed to leave the facility for the purpose of employment or accredited education.

- Work Release – In lieu of incarceration, each participant performs physical labor at a Solano County approved and assigned worksite for approximately 8 hours per day for each day of his/her sentence.

- Electronic Monitoring – Electronic Monitoring is the most intrusive of all the Alternative Custody Programs.  Officers meet with participants weekly to ensure compliance with: curfews, program rules, and conduct random drug tests.

- Supporting the Realignment Plan’s focus on protecting public safety, the Sheriff is working with local police departments to ensure a coordinated law enforcement effort to conduct random compliance checks and other forms of surveillance and monitoring of realigned offenders.  The Sheriff’s Office will expand the existing Recovery Team to find and return to custody those who abscond from other community supervision programs such as Work Furlough and Work Release.

Implementation Update:

The Sheriff’s Enforcement Team (SET) was created in January 2012 to accomplish two primary goals: 1. Complete field compliance checks for offenders placed in the Alternatives To Custody (ATC) program or on Post Release Community Supervision (PRCS).  2. Track down those offenders who have absconded from their respective programs as well as those who have arrest warrants.

In the first two years (2012 & 2013) SET was involved in 856 arrests.  1,296 compliance checks and apprehended 308 fugitives that absconded from their respective programs.

The SET team is composed of 4 Deputy Sheriff’s, 1 Fairfield Police Officer, 2 U.S. Marshals, and a Parole Agent from the Department of Corrections and Rehabilitation.  Personnel on the Team work a variety of assignments including fugitive apprehension, Alternative to Custody (ATC) compliance checks, PRCS compliance checks, PRCS sweeps, sexual offender sweeps, and DUI offender sweeps.  The SET team participated in a total of 32 sweeps during 2013 and assisted in the service of 9 search warrants during the year.  The SET team also conducted a total of 628 compliance checks with 453 or 72% of those compliance checks being directly related to AB-109 realignment.

The SET team assisted the City of Vallejo and the Vallejo Police Department with Operation Goodwill.  Operation Goodwill was a 5 week collaborative operation between the Vallejo Police Department Crime Suppression Unit, the California Highway Patrol, and the Solano County Sheriff’s Office SET team.  During this operation, the team’s combined efforts resulted in 187 arrests, 121 probation searches, 80 traffic citations, and over 600 contacts between citizens and law enforcement.  Seventeen PRCS fugitives were also taken into custody during Operation Goodwill.

Component 4:  Intermediate Sanctions:

- A sanction grid for offenders on PRCS was developed by the CCP to provide consistent sanctions for technical violations that do not rise to the level of filing a petition to revoke with the Court.

Implementation Update

The sanction grid which was developed in 2011 and approved by the Community Corrections Collaborative (CCP) is presently under review to ensure that its implementation comports with the latest research on responding to violations.  Specifically responses to violations should be:

- Shaped by the principles of evidence-based practice and effective interventions;

- Part of an overall supervision strategy that emphasizes reducing the risk of recidivism, enhancing probationer’s success during and following supervision, and using resources wisely;

- Addressed in the context of the probationer’s level of risk to reoffend, the severity of the violation behavior,,the probationer’s criminogenic needs, and other significant stabilizing and destabilizing factors;

- Guided by the policy of the supervision agency in order to assure consistency, even-handedness, and effectiveness across the agency; and

- Characterized by transparency – probationers, agency staff, and the public should be able to understand the rationale for violation responses and see them as part of an agency’s public safety strategies.

Guided by the above principles, a consultant is conducting a review of how Solano County Probation is responding to violation behavior to include PRCS/1170 clients.  The application of the sanctions grid by line staff will be reviewed.  In addition a literature search on responding to client non-compliant behavior will be conducted.  Based on the findings, the consultant will develop a draft policy for how probation officers should respond to and manage client non-compliant behavior.  Upon approval of the policy, the consultant will develop and deliver a staff training program to implement the policy.  Any modifications to the sanction grid developed in 2011 will require approval by the CCP.

Recommendations and Discussion:

Rewards and sanctions shape human behavior.  Although historically sanctions have been used as the primary method to respond to or control an offender’s behavior, research indicates that positive reinforcement should be applied more frequently than negative reinforcement when trying to change behavior.  Part of the reason for this is that many offenders (particularly those at higher risk) have long histories of negative reinforcements and as such, they have learned to adapt to and dismiss the consequences that accompany these responses.  In contrast, research has shown that anti-social individuals (just like the general population) are more likely to repeat behaviors and adopt pro-social attitudes that are recognized, acknowledged, and affirmed, (Gendreau, etal, 1996).

Positive reinforcements do not have to be costly or difficult to administer.  Often, just a word of praise or encouragement can provoke a sense of pride and goodwill and these experiences can increase the likelihood that the pro-social behavior is repeated.  Only a lack of creativity limits our ability to reward and affirm.  The Probation Department has included as part of its review of how client non-compliant behavior is being responded to and sanctions administered the development of an incentives model for offenders placed on probation.  Providing incentives to clients for meeting case-specific goals of supervision is a powerful tool to enhance client motivation and promote positive behavior change.

In 2009 the Administrative Office of the Courts, an agency of the U.S. Federal Courts, conducted a study of the impact of early termination of supervision among federal probationers.  Using a matched sample design, subjects in the early termination and the full-term groups were followed for three years after release, and recidivism was measured on the basis of arrests for new crimes.  Although the subjects of the study were predominately low-risk offenders, moderate and high-risk offenders were represented as well.  Researchers determined that the offenders in the early termination groups, regardless of risk level, had lower rates of recidivism than their full-term counterparts (Baber & Johnson, 2013).  Probation completion that is linked to addressing the client’s assessed criminogenic needs rather than a fixed period of time incentivizes the client’s engagement in risk-reducing interventions. Therefore I recommend that Solano County, with approval from the Court, more formally establish within probation supervision, a presumptive system of earned discharge from probation.  Under this system, probation clients could earn their way off probation prior to the end of their probation term by adhering to and completing case-specific goals, complying with their Court-ordered conditions, and addressing their primary criminogenic needs.  Shortening the period of probation supervision builds on the research that has found that recidivism rates are highest in the first year of placement on probation and release from incarceration, before stabilizing in the second and third year (National Research Council, 2007).

Component 5:  Custody and In-Custody Programs:

- Solano County has received notice of an AB-900 grant award for construction of a new 362-bed jail at Claybank and is proposing a staffing plan that provides for a gradual increase in staff over a period of several years.

Implementation Update

The Sheriff asked for and was awarded 11 allocations for FTE’s in the previous fiscal year’s budget.  They also received an allocation for a Program Manager which has been filled and is proving to be very effective toward program management and development.  There will be additional staff allocations requested as population growth occurs, and expansion points for facility operations are required.

Component 6:  Reentry:

- For reentry as well as to serve those PRCS and 3/non-offenders who come to Solano County with mental health conditions requiring attention, mental health treatment is an important priority for funding in the initial year of realignment.

Implementation Update

Three Mental Health Clinicians are embedded in the Centers For Positive Change (CPC), providing clinical assessments, diagnosis and treatment.  After assessment, clients are triaged into four acuity levels: (1) Specialty level inpatient mental health services provided that medical necessity exists, (2) Specialty level outpatient mental health services with intensive case management wrap-around services provided that medical necessity exists, (3) Specialty level outpatient mental health services provided that medical necessity exists, and (4) if no medical necessity for specialty level mental health services is established, primary care level mental health services are provided.  In addition, outpatient mental health services are provided within the jail.  These services include screening, evaluation, diagnosis, treatment and referral services.  Crisis intervention, grief counseling and management of acute psychiatric episodes can be handled by the on-duty medical staff in the jail with referral to the psychiatric RN and/or access to the psychiatrist on a 24-hour per day basis.

- For reentry as well as to serve those PRCS and 3/non-offenders who come to Solano County with substance abuse issues requiring attention, substance abuse treatment is also an important priority for funding in the initial year of realignment.

Implementation Update

Four Substance Abuse Clinicians are fully integrated in the Center For Positive Change (CPC) providing specialty level group prevention services, assessments and group intervention, as well as face-to-face counseling.  Those clients who are assessed and do not meet medical necessity criteria are referred to primary care level substance abuse services.  Presently the Clinicians have been trained in Matrix Therapy which is an intensive substance abuse outpatient treatment model.  In addition this Fall they will be trained in Treating Addiction Dependence, an intermediate outpatient substance abuse treatment model.  Both programs are Cognitive Behavioral Treatments that have been identified by the Substance Abuse and Mental Health Services Administration as evidence-based treatments.

The Sheriff’s Office currently funds the Solano County Jail Alcohol and Drug Residential Program, delivered by ANKA Behavioral Health.  The “Tools for Transformation” AOD program provides short-term programming for both male and female inmates.  Each program delivers two groups per day, five days per week.  The primary focus of these programs is relapse prevention and generalized substance abuse counseling.  Anger management, trauma and recovery, and parenting skills are also addressed.  All clients also receive individual counseling.

In the near future the Sheriff’s Office will expand Substance Abuse Treatment in the jails to include enhanced, longer term programming for those with substance use disorders who are sentenced offenders.

- For reentry as well as to serve those PRCS and 3/non-offenders who come to Solano County unemployed, education, training and employment-related services are an important priority for funding in the initial year of realignment.

Implementation Update

The CCP launched a pilot project to test what does and does not work in reentry employment services.  Within this project, 5 employment and vocational training vendors provided services to 81 clients between September 1, 2013 and April 1, 2014, resulting in a 31% job placement rate of those clients engaging in services.  These encouraging results have prompted the CCP to triple the service level for FY 2014/15 and the years following.

In this regard, a Request for Proposal (RFP) has been issued to provide comprehensive employment readiness services to both offenders placed on Probation and held in the County Jail.  This RFP is requesting services in the following areas:

- Vocational Training

- Job Development

- Job Placement

- Job Retention

The Sheriff’s Office currently offers a GED Program run by the Solano County Office of Education for both male and female inmates, with or without a high school diploma.  The focus of the GED program is primarily on math, writing, and English skills; students also can work on science and social studies.  Students can prepare for the GED exam, as well as other types of tests such as vocational training and college entrance exams.

In the near future the Sheriff’s Office, in partnership with the Fairfield Suisun Adult School, will launch an Adult Basic Education class for both male and female inmates.  This class will target inmates whose basic education skills are not sufficient enough for them to qualify or participate in the GED class, and who are motivated to improve their skills in preparation for employment or eventual GED study.

In partnership with the Solano County Library, the Sheriff’s Office will also launch a Literacy Tutoring Program in the coming year.  This program will focus on inmates who lack basic literacy skills and will work to enhance reading and writing skills.  The tutor program will provide one-to-one assistance to both male and female inmates.

Currently the Sheriff’s Office is offering an Employability Skills class for female inmates at the Claybank facility.  This class focus is on teaching the soft skills necessary to obtain and maintain employment.  Additionally, inmates learn how to fill out job applications, prepare for interviews, and develop a resume.  At the end of the course, each inmate will have participated in a Mock Interview and receive feedback and will have developed a resume.

In the months ahead, the Sheriff’s Office will be entering into a contract with Michael’s Transportation in order to begin delivering truck driving training and certification to identified inmates.  Additionally, certification training in Forklift Operation will be delivered to selected inmates.

Recently the Sheriff’s Department was awarded a State Grant of approximately $23,000,000 to construct a program facility at the Claybank Campus.  This facility when completed will provide a state of the art classroom and vocational space which will enhance the services available to the inmates housed at this location.  As stated in the original grant proposal, “Solano County’s ultimate goal is to reduce offender recidivism, equip offenders with effective life skills including treatment for mental health needs, and prepare offenders for productive employment.”

- The Reentry Council will be called on to assist with a coordinated reentry approach that can be adapted and/or modified to meet the specific needs of individual offenders while presenting a consistent statement of Solano County’s reentry goals and principles.

Implementation Update

The Sheriff’s Office regularly attends the Reentry Council meetings and has regular planning and development meetings which involve several members/groups represented at the council including: Health and Social Services (mental health, support services, placement services, etc.), Probation, local vocational training providers (Michael’s Transportation, Solano County Building Trades Council, etc.), housing and substance abuse providers (Mission Solano, ANKA, Veterans Administration).

- Agencies involved in realignment have said it would be beneficial for there to be a single point of contact for realignment, a person responsible for reentry coordination, to whom they could go for information about programs and resources that might be used for recommendations and referrals as well as for reentry.  The CCP supports the creation of this position.

Implementation Update

In February of 2014 the Sheriff’s Office hired Renee Smith, LCSW as its Programs and Services Manager. Ms. Smith has spent her initial time coming to understand the Sheriff’s Office and how it interfaces with other departments in Solano County as well as community stakeholders.  Additionally, she is completing an assessment of the existing programs and services within the Sheriff’s Office as well as its reentry system.  Ms. Smith is developing recommendations for the Sheriff and Executive staff regarding how the Department should proceed with respect to augmenting the existing program structure, and creating an evidence-based system of care and coordinated reentry designed to reduce recidivism.

Recommendations and Discussion:

With the hiring of a Programs and Services Manager for the Sheriff’s Office, the establishment and work of the Reentry Council, and the future completion of the program facilities construction project at the Claybank Campus, the County is in a good position to develop a comprehensive reentry model for AB-109/1170 offenders.  Close coordination and shared services between the Sheriff’s Office, the Probation Department, and other key stakeholders is critical for any reentry model to be effective.

Reentry requires collaboration both within the often fragmented correctional arena and also across traditional boundaries to include human service agencies, community organizations, and citizens.  No one can do this alone, least of all correctional agencies.  Agencies whose mission it is to provide substance abuse services, to enhance employability and employment rates, to provide education, to provide health care financing and services and to provide mental health services all have a reason to be at the table.  The work of the CCP has established the framework for this to occur.

Due to the recognition of the importance of reentry for maintaining public safety, there has been over the past decade, a number of national efforts to improve practice in this area.  The National Governor’s Association Reentry Policy Academy; the Council of State Governments’ Reentry Policy Council; the Serious and Violent Offender Reentry Initiative (SVORI); the President’s Prisoner Reentry Initiative (PRI) of the U.S. Justice Department, Bureau of Justice Assistance; and the JEHT Foundation’s support of reentry efforts, all underline the importance of reentry as a public policy issue.  All of these efforts converge and reinforce one another on many levels.  Parallel to these efforts has been the seminal work of the Department of Justice National Institute of Corrections in their Transition from Prison to the Community (TPC) Initiative.  The culmination of this initiative was the publishing of the TPC Reentry Handbook in 2008, a companion document to Increasing Public Safety Through Successful Offender Reentry and the TPC Case Management Handbook.

A cornerstone of the TPC initiative is the development of an Integrated Case Management and Supervision Model to serve as the framework for successful offender reentry.  There are eight core principles upon which the Model is based, (NIC, 2008):

- Supervising and managing offenders to enhance successful transition and reentry for community safety.

- Engaging case management and supervision from admission to jail (or before) through discharge to the community (and beyond) in a coherent and integrated process.  The largely fragmented process now in existence involves significant disconnects between what happens to offenders in jail and what happens after they are released to supervision.

- Using the principles of evidence-based practice.  This principle demands that policymakers use the lessons emerging from the research to shape their practices and use of resources, as specified in the next two principles.

- Basing supervision and case management plans on empirically based and validated assessments of risk and criminogenic need.  This principle requires a commitment to selecting and implementing assessment protocols that are valid, reliable, and normed to a jurisdiction’s populations.

- Targeting supervision and case management by risk and needs to have maximum impact on reducing recidivism and enhancing community safety.  This principle implies that choices will need to be made about where to use resources, with some offenders receiving proportionately more supervision / treatment and others receiving less.

- Engaging the offender in the process of change by using supervision and case management interactions to enhance motivation.  This principle implies that efforts will be made to engage offenders in the process of change during the course of incarceration and post release supervision.

- Defining supervision and case management as a collaborative process that involves correctional staff (both institutional staff and field/community staff), community service providers, and informal networks of support such as families, mentors, employers, and associates.  Such collaboration requires the close integration of efforts within correctional institutions with efforts in the community and also the involvement of non-criminal justice partners at all stages of the process.

- Forming multidisciplinary supervision and case management teams to work with the offender through assessment, case planning, and implementation.  This requires that, at the case level, correctional staff work collaboratively with others in a team approach to supervision and case management.

Given the above principles, there are six (6) primary activities that are essential to successful implementation, (NIC, 2008):

- Conduct assessments of offenders’ risks, needs, strengths, and environment.

- Form, participate in, and lead case management teams that work collaboratively.

- Develop and implement, along with offenders and other partners within both correctional and other agencies, a transition accountability plan geared directly to the level of offender risk and the criminogenic needs.

- Provide or facilitate access to programs and interventions to address risk and needs.

- Involve offenders in the case management process and engage them in the process of change, making efforts to enhance their motivation (e.g., by using incentives for positive performance).

- Review progress and adapt plans accordingly over time.

For many jurisdictions, these activities are a radical departure from past practices that cast line staff primarily in a monitoring function, whether that be monitoring behavior and compliance with institutional rules by custody staff in institutions, or monitoring behavior and compliance with conditions of supervision by supervision staff in the community.

The work of NIC should guide the development and implementation of Solano County’s reentry model.  The above principles and activities have already been incorporated within Solano County’s Centers for Positive Change.  The hiring and training of sufficient Case Managers / Caseworkers is critical to successful offender reentry.  Therefore I would recommend that the Sheriff’s Office establish a sufficient number of Case Manager positions either through additional FTE or service contracts, to carry out the above activities with the confined AB-109/ 1170 inmates.  Because the majority of these offenders are high risk with multiple needs, at the CPC the number of clients assigned to each CPC Caseworker was capped at 25.  The Caseworkers at the CPC also have been trained to conduct client group programming.  A similar model should be considered by the Sheriff’s Office.

When providing programming for 1170 inmates who have a period of mandatory supervision following their jail term, a seamless handoff of the client to the Probation Department should be established.  We know from the research that when the same program models are conducted within a correctional facility and also in a community setting, the community program achieves better client outcomes.  This is particularly the case in Cognitive Behavioral Treatment that focuses on restructuring the client’s criminal thinking, and then providing the client with new decision-making and problem-solving sills.  Giving the client an opportunity to practice these skills in their natural environments while exposing them to prosocial supports is more likely to occur within the community than in a correctional facility.  Therefore, for 1170 inmates with mandatory supervision, their education, vocational, and mental health needs should be addressed if possible, while they are in jail.  Client engagement and motivational enhancement services which are preparatory to addressing other criminogenic needs should also be provided.  In addition, addressing basic needs like housing, transportation, and any social services entitlements should be dealt with prior to their return to the community. However for these clients, addressing any anti-social values and attitudes, anti-social peers, and substance abuse, would likely be more successful while they are serving their term of probation.  Programs that focus on each of these need areas are available at the Centers For Positive Change.

1170 inmates who do not have any mandatory community supervision will need to have access to all the above services while they are confined at the jail.  Furthermore, in order to provide them with a period of supervision while in the community, the Sheriff’s Office should look to expand their Alternative to Custody Programs to this population.  The Sheriff’s ATC Officers supervising this population should both monitor participant compliance and facilitate positive behavior change.  To assist the officers in this role, they should receive training in Motivational Interviewing and Effective Practices in Correctional Settings II.  Two documents that should prove useful to the Sheriff’s Office in the development of the AB-109 reentry program have been included in Appendix E of this Report.

Component 7:  Service Delivery Strategies:

- Realignment is committed to using proven effective and cost effective service delivery strategies to manage offenders realigned to its custody.  Service Centers and Day Reporting Centers are among the most widely researched, proven effective and cost effective rehabilitative service delivery strategies in use today.

Implementation Update

At the July 11, 2012 CCP meeting, direction was provided to explore the creation of a Center For Positive Change (Services Center) in Vallejo and in Fairfield.  Four Operational Workgroups were established to refine the service delivery model in the following areas:

- Cognitive Behavioral Groups and Drug Testing: Probation

- MH / Substance Abuse Assessments, Treatment and Benefit services: HSS

- GED / High School, Job Readiness and Vocational Training: WIB and Sheriff’s Office

- Housing: Reentry Council

In August the CCP secured the services of a consultant to assist in the development and implementation of the CPC.  During the consultant’s initial onsite visit he met individually and collectively with members of the CCP Executive committee, Workgroup Chairs, and identified stakeholders.  It was evident that a significant amount of thought and work had gone into the development of the CPC by the members of the workgroups.  The consultant’s final report which was approved by the CCP Executive Committee in February of 2013 reflected many of the ideas of the Four Operational Workgroups.  Presently the Centers For Positive Change (CPC) in Vallejo and Fairfield are operating at capacity with approximately 75 clients at each location.  A permanent location has been established for the CPC in Vallejo while the Fairfield CPC is operating out of the Probation Department until a permanent location is established.  A summary description of the CPC program can be found in Appendix F of this Report.

Recommendations and Discussion:

A core component of the CPC program model and framework was the establishment of a sufficient number of Caseworkers who could provide weekly supportive counseling to a caseload of 25 clients, as well as conduct evidence-based group interventions.  For this to occur, the Clinical Services Associates (CSA) assigned to the CPC by Health and Social Services (HSS) would need to serve as Caseworkers along with the assigned Deputy Probation Officers (DPO).  To effectively carry out this function, they need to develop client Case Plans, maintain individual client case notes, and be able to share that information with other members of the client’s treatment team.  For clients placed on probation this information needs to be entered into and maintained in the Probation Department’s Case Management System (CASE).

At this point it has been determined that due to privacy and confidentiality regulations, the CSAs cannot be given access to CASE.  This is hindering their ability to effectively carry out these critical Caseworker responsibilities.

The CPC program model also required Caseworkers to follow a specific client interaction model and receive quality assurance coaching from the CPC Supervisor or a trained coach.  This is accomplished by audiotaping selected Caseworker client contacts and interactions.  A question raised by the CSA’s asserts that due to client confidentiality and HSS regulations, this form of coaching by the CPC Probation Supervisor is not possible, nor could a non-licensed individual provide them with clinical supervision.  The above issues if not addressed, will seriously undermine the integrity of the CPC program model and negatively impact the program’s effectiveness.

In addition the CSAs are running Matrix Therapy Groups which require weekly support meetings with each client in the group.  This is in addition to their weekly individual client meetings with the 25 clients on their caseloads.  Furthermore, they are conducting lengthy clinical assessments (ASI’s) on CPC clients referred to intensive outpatient treatment and all AB-109 clients that the Court is referring to a residential treatment program.  Also, the CSAs will soon be trained in an intermediate substance abuse treatment model that they will be conducting for CPC clients in addition to Matrix Therapy Groups.  These functions are important program components that will require a workload level for the CSAs that was not anticipated in the initial program design.  Due to all of these issues a re-examination of the CPC staffing allocation is required.  In order to address these issues the CSA Caseworker’s responsibilities need to be removed.  I am therefore recommending that the senior DPO in the Fairfield CPC be assigned a client caseload of 25 clients, and an additional senior APO position be assigned to the Vallejo CPC to serve as a Caseworker as well as to provide an on-site supervisory presence which is needed in the absence of the CPC Supervisor who oversees both CPCs and alternates between Fairfield and Vallejo.  This action will allow the CSAs to focus all of their time on their clinical responsibilities which are both critical and substantial.

The staff at the CPCs reported that many of their clients are either homeless or lack stable and appropriate housing.  Furthermore they report that there are insufficient available shelter beds within the County to serve this client population.  A more systematic review needs to be conducted to determine the extent of this problem.  Depending upon the results, the County should establish in strategic locations a number of transitional beds for use by the CPC staff to help address this issue.  These beds would provide stable temporary shelter while the CPC and Probation supervision staff work with the client on locating a more permanent residence.  It will be important that any established beds remain transitional with a limited length of stay for each individual client.  These beds would not be the solution to the long-term housing needs of these clients which should also be further examined.  For Fiscal Year 2014/15, $150,000 has been allocated to be used for the above purpose.  Further study will help determine whether or not this is a sufficient allocation.

When the CPC program framework was initially developed, approximately 8% of the AB-109 clients on probation supervision were female.  Based upon these numbers the CPC program model did not focus on the unique needs of female clients.  Female offenders face issues specific to their gender.  These often include histories of childhood and adult physical and sexual abuse, and ongoing primary caregiving responsibilities.  Incarcerated females are more likely to have been the victim of physical or sexual abuse than incarcerated males.  Female offenders are less likely to have significant criminal histories, commit murder, or a violent offense against a stranger.  Their crimes are often relationally oriented or committed against someone with whom they previously had a relationship.

The majority of incarcerated female offenders have a drug or substance abuse problem.  They also evidence high rates of trauma and physical and mental health issues.  They often come to the criminal justice system with depression, post-traumatic stress disorder, poor nutrition habits, reproductive issues, and high-risk pregnancies.  It is not enough to apply or adapt programs designed for male offenders to female offenders.  It is crucial that programs are built and designed around the central needs, life trajectories, and victimization histories of women.  Female clients should not be at the CPC with male clients, nor placed in treatment groups with male clients.  Although there is a gender-specific treatment group presently being conducted at the CPC, a closer examination of how services are being provided to AB-109 female clients, as well as how they are being assessed should be conducted.

Implementation Element 1:  Training

- Realignment is new, complex and evolving, and therefore will necessitate ongoing training for the Courts, District Attorney’s Office Public Defender’s Office, Probation Officers, Sheriff’s personnel, Police Officers, service providers and others involved in its implementation.  The CCP supports continuous and ongoing training.

Implementation Update

Since the completion of the 2011 Implementation Plan the following training specific to implementing AB-109 has been provided:

- Public Defender’s Staff – The Public Defender’s Office had two 4-hour trainings in late 2011 and again in 2012.  A manual has been developed for all Public Defenders and is regularly reviewed by staff.

- Health and Social Services Staff – Extensive training was provided in gender-specific, trauma informed case management by Dr. Stephanie Covington.   HSS, the Probation Department, Solano Community College, Workforce Investment staff, as well as vendors providing employment services were trained in the Roots for Success Vocational Training Program by Dr. Raquel Pinderhughes.

- Sheriff’s Office Staff – Sheriff’s staff attended two related trainings in 2013; Pretrial Justice and Realignment Implications for County Criminal Justice Systems; and Integrating Resources for Achieving Successful Outcomes for Justice Involved Individuals.

- District Attorney’s Staff – The District Attorney’s Office has provided training on realignment to their attorneys on several occasions since the implementation of Realignment.  The most recent training was on March 31, 2014, when they invited Deputy District Attorney Lisa Rodriguez from the San Diego County District Attorney’s Office to their office to conduct a 3-hour training presentation on Realignment.

- Probation Department’s Staff – Probation staff responsible for Realignment implementation and/or working with AB-109 clients have attended the following related training:

- Annual Conference on Public Safety Realignment

- Changing Offender Behavior

- AB-109 Basics and Funding

- Felony Sentencing After Realignment

- Practical Guide to Incentives and Sanctions

- Practical Guide to Incentives and Sanctions

- Supervising Offenders with Mental Health and Substance Abuse Treatment Needs

- Level of Services Case Management Inventory

- Adult Substance Use Survey

- Client Case Classification and Supervision

- Effective Practices in Community Settings

- Reasoning and Rehabilitation II

- Think For A Change

- Matrix Therapy

- Facilitating Treatment Groups

- Courage To Change Journals

- Treating Addiction Dependence (October 2014)

Implementation Element 2:  Communication

- Local police departments and the Sheriff’s Office have convened a workgroup to develop systems and procedures to share data so that among other things, officers on the street will know when they are dealing with realigned offenders.

Implementation Update

Working with Solano County Dispatch, Solano County Probation, and State Parole, the Sheriff’s Department was able to expand the wanted person’s system to include PRCS warrants in CLETS.  Now, when any dispatch center runs a name through the data system, a “hit” is created showing the PRCS status of the individual on the program.

- Public education will be undertaken as implementation goes forward to explain realignment and what is being done to ensure public safety during this correctional paradigm shift.

Implementation Update

The Sheriff and Chief Probation Officer have both made numerous presentations to civic groups in Solano County.  The County has placed on its public website CCP meeting minutes, as well as all AB-109 reports.  The CCP has until recently, conducted monthly meetings that were open to the public, and moving forward the CCP is meeting quarterly.  In addition, two (2) public forums were held in Vallejo to provide information on the CPC and obtain public comment.

Implementation Element 3:  Evaluation and Quality Control

- The CCP will monitor and track the implementation progress of and outcomes produced by its realignment efforts.  It will track the recidivism outcomes required by AB-109 and will monitor and report data about offenders on PRCS similar to what is required to be reported about CCPIA (SB678) clients, including but not limited to:

- The number who successfully complete their PRCS

- The number with new offenses

- The number with new felony convictions

- The number of revocations

Implementation Update

The County is maintaining data on all AB-109 clients.  New convictions occurring within Solano County are being tracked as well as revocations that result in a return to custody.  The Probation Department employed a full time position to assist in data collection and evaluation of the Probation Department’s AB-109 initiatives.  A lack of an integrated automated information technology system within and between County agencies coupled with difficulties in collecting, retrieving, and analyzing data continues to be a major roadblock to establishing performance-based management systems, and a sound evaluation protocol.

Split Sentencing Recommendation:

Although monitoring offenders when they leave prison or jail may seem like common sense, there was little research until recently on the question of whether community supervision effectively reduces recidivism.  Research is now beginning to show that inmates released to community supervision are more likely to have better public safety outcomes than those who max out.  These results demonstrate that supervision, when implemented with fidelity to evidence-based practice, can reduce crime and corrections costs.

One recent study in New Jersey found that parolees have better public safety outcomes than inmates who serve their full sentences.  Among offenders released in 2008, fewer parolees than max-outs were rearrested (51% vs. 65%), reconvicted (38% vs. 55%), or returned to prison for a new crime (25% vs. 41%) within 3 years of release.  Even controlling for key risk factors such as age, time served, and criminal history, did not diminish the benefits of supervision.  Parolees were still 36% less likely to return to prison for new crimes, (The Impact of Parole in New Jersey, 2013).

Policymakers are increasingly recognizing the fragility of the successful resumption of community life after incarceration.  States and the federal government are committing significant resources to improve reentry planning and strengthen community supervision in response to evidence of their effectiveness in protecting public safety by preventing recidivism.

It would be in the best interest of public safety if a period of community supervision by the Probation Department was part of every AB-109/1170 sentenced to the County Jail (split sentence).  Within the framework of just desserts, proportionality and fairness, AB-109/1170 offenders who are not placed directly on probation, should after a period of incarceration  (when possible not to exceed 3 years before time credits), be supervised in the community for 12 to 24 months. Providing a period of supervision for every sentenced offender released from the County Jail will enhance the safety of the County’s residents.

CONCLUSION

The Executive Committee of the CCP, its standing members, County and Agency Administrators, and County elected officials are to be commended for the actions they have taken to implement AB-109, the 2011 Public Safety Realignment Act.  Their hard work and commitment to improving public safety for the residents of Solano County was evident to the author during this review process.  The vast majority of the recommended activities contained in the 2011 Implementation Plan have been implemented.  As suggested within this Report, there are some additional refinements that can be made, and in the author’s opinion, some new initiatives that should be pursued.  It will take time for new programs to achieve their desired outcomes.  However, if implemented with fidelity and integrity to the research informed models that have and continue to be developed within Solano County, the goal of reduced offender recidivism will be realized.  When this occurs all of the residents of Solano County will be the beneficiaries.

RECOMMENDATIONS SUMMARY *

- To achieve the Sheriff’s Office objective of assessing an inmate’s suitability for the ATC program, informing placement into appropriate programming, and supporting the development of an inmate reentry plan, more than the LS/CMI should be administered.  I would recommend that a mental health screen and substance abuse screen also be administered as soon as possible after the inmate has been placed in jail.

- The LS/CMI and the ASUS-R are robust assessment tools that have been validated and normed to national criminal populations.  Although they have proven to be predictive throughout the United States, they should also be validated and normed to a representative sample of offenders residing in Solano County.

- To ensure there is congruency between staff who are administering the LS/CMI, inter-rater reliability tests need to be conducted at least on an annual basis.

- A brief risk screen should be administered to all probationers convicted of domestic violence.  The results of the screen coupled with the results of the LS/CMI should inform the intensity of probation supervision.

- The Pretrial Justice Institute which was founded in 1977 has identified six core functions of a pretrial services program that were derived from national standards.  In developing a pretrial program for Solano County, these standards should be followed as closely as possible.

- A full time staff coach who has been trained in both MI and EPICS would be a sound investment for the County and the Probation Department to ensure that the probation staff trained in these evidence-based models are using them effectively when working with their clients.

Solano County should more formally establish within probation supervision, a system of earned discharge from probation.  Under this system, probation clients could earn their way off probation prior to the end of their probation term, by adhering to and completing case-specific goals, complying with their Court-ordered conditions, and addressing their primary criminogenic needs.

* These recommendations should be reviewed and considered within their context in the Full Report.

- The work of the National Institute of Corrections should guide the development and implementation of Solano County’s reentry model.

- The Sheriff’s Office should establish a sufficient number of Case Manager positions either through additional FTE or service contracts, to carry out the casework functions with the confined AB-109/1170 inmates.  Because the majority of these offenders are high-risk with multiple needs, at the CPC the number of clients assigned to each CPC Caseworker was capped at 25.  The Caseworkers at the CPC also have been trained to conduct client group programming.  A similar model should be considered by the Sheriff’s Office.

- For 1170 inmates with mandatory supervision, any education, vocational, and mental health needs should be addressed if possible, while they are in jail.  Client engagement and motivational enhancement services which are preparatory to addressing other criminogenic needs should also be provided.  In addition, addressing basic needs like housing, transportation, and any social services entitlements should be dealt with prior to their return to the community. However for these clients, addressing any anti-social values and attitudes, anti-social peers, and substance abuse, would likely be more successful while they are serving their term of probation.  Programs that focus on each of these need areas are available at the Centers for Positive Change.

- 1170 inmates who do not have any mandatory community supervision should have access to all the needed services while they are confined at the jail.

- In order to provide 1170 inmates who do not have a term of probation with a period of supervision when returning to the community, the Sheriff’s Office should look to expand their Alternative to Custody Programs to this population.

The Sheriff’s ATC Officers supervising this population should both monitor participant compliance and facilitate positive behavior change.  To assist the officers in this role, they should receive training in Motivational Interviewing and Effective Practices in Correctional Settings II.

* These recommendations should be reviewed and considered within their context in the Full Report.

- The senior DPO in the Fairfield CPC should be assigned a client caseload of 25 clients, and an additional senior APO position should be assigned to the Vallejo CPC to serve as a Caseworker as well as to provide an on-site supervisory presence in the absence of the CPC Supervisor who will oversee both CPCs and alternate between Fairfield and Vallejo.

- Female clients should not be at the CPC with male clients, nor placed in treatment groups with male clients.

- A systematic review needs to be conducted to determine the transitional housing needs of the AB-109/1170 clients.  Depending upon the results, the County should establish in strategic locations, a number of transitional beds for use by the CPC staff to assist their clients who have this need.

- A closer examination of how services are being provided to AB-109 female clients, as well as how they are being assessed should be conducted.

- It would be in the best interest of the residents of Solano County if a period of community supervision by the Probation Department was included in every AB-109/1170 sentenced to the County Jail.  Within the framework of just desserts, proportionality and fairness, AB-109/1170 offenders who are not placed directly on probation, should after a brief period of incarceration, be supervised in the community for 12 to 24 months.

* These recommendations should be reviewed and considered within the context of this Report.

* These recommendations should be reviewed and considered within their context in the Full Report.

REFERENCES

Andrews, D.A., & Bonta, J. (2010).

The psychology of criminal conduct (5th ed.). New Providence, NJ: LexisNexis Mathew Bender.

Baber, L.M. & Johnson, J.L. (2013)

Early termination of supervision: No compromise to community safety.  Federal Probation, 77(2).

Gendreau, P., Little, T. and Groggin C. (1996)

A meta-analysis of adult offender recidivism: What works? Criminology, 34(4): 575-607.

Joyce, B., and Showers, B. (2002)

Student achievement through staff development, Alexandria, VA: ASCD

Laura and John Arnold Foundation.

Pretrial Criminal Justice Research, November 2013

Miller, WR, Mount, KA.

A small training in motivational interviewing:  Does one workshop change clinician and client behavior?  Behavioral and Cognitive Psychotherapy 2001; 29:457-471

National Institute of Corrections.

The TPC Reentry Handbook: Implementing the NIC Transition from Prison to Community Handbook. (2008).

National Research Council.

Parole, Desistance from Crime, and Community Integration

(Washington: National Academics Press, 2007).

The Pew Charitable Trusts, Pew Center on the States.

Time Served: The High Cost, Low Return of Longer Prison Terms. (June 2012).

Pretrial Justice Institute.

Pretrial Services Program Implementation: A Starter Kit, 2010

Rudes Danielle S., etal. (2011)

Adding positive reinforcement in justice settings: Acceptability and Feasibility.  Journal of Substance Abuse Treatment.